## Sheet1
To be completed Week ending | 2013-09-01 | 2013-09-08 | 2013-09-15 | 2013-09-22 | 2013-09-29 | 2013-10-06 | 2013-10-13 | 2013-10-20 | 2013-10-27 | 2013-11-03 | 2013-11-10 | 2013-11-17 | 2013-11-24 | 2013-12-01
Phase 1 Pre-project work | bar: 2013-09-01 to 2013-09-08
Phase 2 Collaborate to design new process | bar: 2013-09-15 to 2013-09-22
Set up meeting with Julie | bar: 2013-09-15
Install new software | bar: 2013-09-22
Phase 3 Test | bar: 2013-09-29 to 2013-10-06
Design a testing schedule | bar: 2013-09-29
Get agreement with teams to do test | bar: 2013-09-29
Communicate with other teams the test is going ahead | bar: 2013-09-29
Do analysis of test results | bar: 2013-10-06
Phase 4 Get agreement with "Bob" on new process | bar: 2013-10-13 to 2013-10-20
Phase 5 Pilot | bar: 2013-10-27 to 2013-11-17
Phase 6 Sign-off | bar: 2013-11-24
Phase 7 Review | bar: 2013-12-01
Note on A2: Stephen Mather: Includes first four elements of the Simple Improvement Process: Identifying business reason why, current state analysis including collecting data and root cause, generate SMART goal, plan project including this Gantt Chart
Note on A3: Stephen Mather: You probably can't create this until you have completed phase 1. These will be specific to the project and you may need a few more than 6 or 7. Don't get too much into the detail though. Ideally for bigger projects you might want to have a little Gantt chart for each phase which might have a different owner. You can get clever in Excel with different levels of detail that you can drill into keeping it on one sheet.